## BASE BID (hidden)
PROJECT :AQOURA NATIONAL TRAINING OPERATIONS CTR LE-496243
BILL OF QUANTITIES | [5 empty] | Internal House Estimate | [8 empty] | Yammine |  | Rayan Fawaz
ITEM REF. | DESCRIPTION | QUANTITY | UNIT | RATE | AMOUNT | LABOUR MANHOURS | DIRECT LABOR COST | DIRECT EQUIPMENT COST | DIRECT MATERIALS COST | DIRECT SUB CONTRACTOR COST | TOTAL DIRECT COST | OVERHEAD/ INDIRECT COST | PROFIT | TOTAL PROPOSED COST | RATE | AMOUNT | RATE | AMOUNT
0001 | Mobilization and Demobilization at the Concrete Maintenance Pad Area in Accordance with the Contract Documents | [9 empty] | 42500 |  |  |  |  | 22000 |  | 39500
0001AA | Mobilization at the Concrete Maintenance Pad Area in Accordance with the Contract Documents |  |  |  |  | 32 | 500 | 1000 | 5000 |  | 6500 |  |  |  |  | 6500 |  | 6500
0001AB | Demobilization at the Concrete Maintenance Pad Area in Accordance with the Contract Documents |  |  |  |  | 32 | 1000 | 2000 |  |  | 3000 |  |  |  |  | 3000 |  | 3000
The Contractor is referred to the specification and drawings for all details related to the works of this division and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the items
0002 | Concrete Maintenance Pad Construction in Accordance with the Contract Documents | [9 empty] | 37504 |  |  |  |  | 21155 |  | 38574
Construct concrete Maintenance Pad
A | Subgrade preparation | 480 | m2 |  |  | 96 | 960 | 960 |  |  | 1920 |  |  |  | 2.5 | 1200 | 5 | 2400
B | 150mm Portland Cement Concrete | 65.4 | m3 |  |  | 120 | 2943 | 981 | 6540 |  | 10464 |  |  |  | 85 | 5559 | 240 | 15696
C | 150mm Aggregate Base Course | 436 | m2 |  |  | 108 | 872 | 872 | 7412 |  | 9156 |  |  |  | 4.5 | 1962 | 15 | 6540
D | 300mm Compacted Subgrade | 436 | m2 |  |  | 96 | 2616 | 2180 |  |  | 4796 |  |  |  | 9 | 3924 | 15 | 6540
E | Allowance for excavation | 480 | m2 |  |  | 120 | 720 | 1440 |  |  | 2160 |  |  |  | 3 | 1440 | 6 | 2880
Concrete Accessories
Dowel to Construction Joint
A | Allowance for Epoxy coated Dowel bar dia. 19 bar x 400mm length @ 300mm c/c in PCC 150mm thick (drawing ref CS502), sawcut 3mm per 50mm thick | 292 | unit |  |  | 48 | 2044 |  | 3504 |  | 5548 |  |  |  | 15 | 4380 | 4 | 1168
B | Thickened edge | 22 | unit |  |  | 24 | 440 |  | 770 |  | 1210 |  |  |  | 20 | 440 | 50 | 1100
C | Contraction Joint | 90 | lm |  |  | 32 | 1800 |  | 450 |  | 2250 |  |  |  | 25 | 2250 | 25 | 2250
0003 | Concrete Maintenance Pad Area Sitework in Accordance with the Contract Documents | [9 empty] | 49887.5 |  |  |  |  | 56612 |  | 55560
0003AA | Survey & Design for all Sitework Related to the Concrete Maintenance Pad Area in Accordance with the Contract Documents | [9 empty] | 34000 |  |  |  |  | 46000 |  | 36000
| Survey & Design for all Sitework Related to the Concrete Maintenance Pad Area | 4000 | M2 |  |  | 128 | 12000 | 2000 | 4000 |  | 18000 |  |  |  | 9.5 | 38000 | 4 | 16000
| Grading of external area | 4000 | M2 |  |  | 280 | 6000 | 10000 |  |  | 16000 |  |  |  | 2 | 8000 | 5 | 20000
0003AB | Construct Concrete Maintenance Pad Area Sitework in Accordance with the Contract Documents | [9 empty] | 15887.5 |  |  |  |  | 10612 |  | 19560
Specification Section 32 12 15.00
Proposed Access Road
Aggregate Pavement Section
A | Subgrade preparation | 525 | m2 |  |  | 48 | 1050 | 1050 |  |  | 2100 |  |  |  | 2.5 | 1312.5 | 5 | 2625
B | 150mm Aggregate Surface Course | 79 | m3 |  |  | 72 | 158 | 158 | 1659 |  | 1975 |  |  |  | 28 | 2212 | 15 | 1185
C | 150mm Aggregate Base Course | 525 | m2 |  |  | 48 | 787.5 | 262.5 | 8925 |  | 9975 |  |  |  | 4.5 | 2362.5 | 15 | 7875
D | 300mm Compacted Subgrade | 525 | m2 |  |  | 48 | 1050 | 787.5 |  |  | 1837.5 |  |  |  | 9 | 4725 | 15 | 7875
| Additionals (with mobilization) | [9 empty] | 33000 |  |  |  |  | 12500 |  | 30000
| Allowance for Generator | 1 | item | [7 empty] | 18000 |  |  |  | 12000 | 12000 | 20000 | 20000
| Allowance for required water tank | 1 | item | [7 empty] | 15000 |  |  |  | 500 | 500 | 10000 | 10000
| Total CLINs 0001-0003 | [9 empty] | 129891.5 |  |  |  |  | 99767 |  | 133634
0004 | VAT Taxes (CLINS 0001-0003) | [9 empty] | 14288.065 |  |  |  |  | 10974.37 |  | 14699.74
| Carried to Collection | [5 empty] | 31997.5 |  |  |  | 129891.5 |  |  |  |  | 99767 |  | 133634
[11 empty] | 129891.5 |  |  |  |  | 99767 |  | 133634
| DBA (10%) | [5 empty] | 3199.75

## Option 2 (hidden)
PROJECT :AQOURA NATIONAL TRAINING OPERATIONS CTR LE-496243
BILL OF QUANTITIES | [5 empty] | INHOUSE ESTIMATE | [8 empty] | Shwaifaty |  | Mezher Steel |  | Alutop |  | Yammine |  | Rayan Fawaz
ITEM REF. | DESCRIPTION | QUANTITY | UNIT | RATE | AMOUNT | LABOR MAN-HOURS | DIRECT LABOR COST | DIRECT EQUIPMENT COST | DIRECT MATERIALS COST | DIRECT SUB CONTRACTOR COST | TOTAL DIRECT COST | OVERHEAD/ INDIRECT COST | PROFIT | TOTAL PROPOSED COST | RATE | AMOUNT | RATE | AMOUNT | RATE | AMOUNT | RATE | AMOUNT | RATE | AMOUNT
0005 | CMU Demonstration Building & Site Construction in Accordance with the Contract Documents | [9 empty] | 293930.3148 | [10 empty] | 272569.7449
The Contractor is referred to the specification and drawings for all details related to the works of this division and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the items
0005AA | Mobilization
0005AA | Mobilization at the CMU Demonstration Building Area in Accordance with the Contract Documents | 1 | Item |  |  | 128 | 2000 | 2500 | 12000 |  | 16500 | [9 empty] | 32000 | 32000 |  | 64000
0005AB | Demobilization
0005AB | Demobilization at the CMU Demonstration Building Area in Accordance with the Contract Documents | 1 | Item |  |  | 112 | 1400 | 300 |  |  | 1700 | [9 empty] | 5000 | 5000 |  | 10000
0005AC | CMU Demonstration Building Construction in Accordance with the Contract Documents | [9 empty] | 183155.0854 | [10 empty] | 166591.3288 |  | 196597.7192
Construct CMU Demonstration Building
Construct Concrete Slab
Excavation
A | Excavation for foundation; all in accordance with the drawings and specification | 324 | m3 |  |  | 32 | 259.2 | 1134 | 162 |  | 1555.2 | [9 empty] | 4 | 1296 | 6 | 1944
Disposal
B | Disposal of excavated surplus material from site to approved location all in accordance with the drawings and specification | 178 | m3 |  |  | 6 | 178 | 267 | 195.8 |  | 640.8 | [9 empty] | 1 | 178 | 5 | 890
Backfilling
C | Backfilling in making up levels with selected excavated materials; in compliance with the Specification and subject to the Contracting Officer's approval | 216 | m3 |  |  | 40 | 324 | 324 | 1296 |  | 1944 | [9 empty] | 2 | 432 | 3 | 648
Shoring
G | Shore the existing surface prior to excavation, including to retain a Professional Engineer, Finish shoring, including sheet piling, and install as necessary to protect workmen, banks, adjacent paving, structures, and utilities | 82.05 | m2 |  |  | 64 | 6153.75 | 6974.25 | 6564 |  | 19692 | [9 empty] | 140 | 11487 | 200 | 16410
Capillary Barrier Base Material
E | 200mm thick crushed stone capillary barrier min 760mm all in accordance with the drawings and specification | 124.64 | m3 |  |  | 32 | 249.28 | 436.24 | 2368.16 |  | 3053.68 | [9 empty] | 32 | 3988.48 | 30 | 3739.2
F | 100mm thick capillary vapor barrier all in accordance with the drawings and specification | 16.4 | m3 |  |  | 16 | 123 | 106.6 | 377.2 |  | 606.8 | [9 empty] | 32 | 524.8 | 30 | 492
Anti-Termite Treatment
G | Anti-termite treatment all in accordance with the drawings and specification | 280 | m2 |  |  | 32 | 140 |  | 840 |  | 980 | [9 empty] | 1 | 280 |  | 980
Dewatering
H | Allowance for installation and maintenance of Dewatering System | 30 | day |  |  | 60 | 166.6667 | 45000 | 1500 |  | 46666.6667 | [9 empty] | 3000 | 90000 |  | 46666.6667
CONCRETE WORKS
The Contractor is referred to the specification and drawings for all details related to the works of this division and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the items
SUBSTRUCTURE
SECTION 03 30 00
Cast-in Place Concrete
Reinforced concrete 28 Mpa, design mix as per the drawings and specification ( General notes 3 drawing ref SB100)
A | Footing | 58.5 | m3 |  |  | 24 | 877.5 | 350 | 4095 |  | 5322.5 | [9 empty] | 85 | 4972.5 | 150 | 8775
B | Foundation Stem Wall | 10.5138 | m3 |  |  | 4 | 157.7063 | 70 | 735.9625 |  | 963.6688 | [9 empty] | 85 | 893.6688 | 190 | 1997.6125
C | 150mm Thick Slab | 24.6 | m3 |  |  | 6 | 295.2 | 140 | 1722 |  | 2157.2 | [9 empty] | 85 | 2091 | 150 | 3690
D | Concrete stoop size:2100x400mm | 2 | ea |  |  | 2 | 70 | 70 | 140 |  | 280 | [9 empty] | 95 | 190 |  | 280
Concrete Reinforcing
Reinforcing steel deformed bars of all diameters, ASTM A615, Grade 460 UNO, all in accordance with the drawings and specification. ( General notes 2 drawing ref SB100)
| T16 Reinforcing bars diameters in Footing | 1150 | kg |  |  | 64 | 287.5 | 115 | 862.5 |  | 1265 | [9 empty] | 1 | 1150 | 1 | 1150
| T16 Reinforcing bars diameters in Stem Wall | 410 | kg |  |  | 24 | 102.5 | 41 | 307.5 |  | 451 | [9 empty] | 1 | 410 | 1 | 410
| Reinforcing bars diameters Ø16 BAR AT 450mm O.C. EACH WAY, CENTERED IN SLAB | 1470 | kg |  |  | 80 | 367.5 | 147 | 1102.5 |  | 1617 | [9 empty] | 1 | 1470 | 1 | 1470
Structural Cast-in-Place Concrete Forming
Formwork all in accordance with the drawings and specification.
| To Footings | 306 | m2 |  |  | 64 | 1530 |  | 4590 |  | 6120 | [9 empty] | 4 | 1224 | 8 | 2448
| To stem walls | 94.94 | m2 |  |  | 48 | 474.7 |  | 1424.1 |  | 1898.8 | [9 empty] | 15 | 1424.1 | 8 | 759.52
| To slab | 172.25 | m2 |  |  | 24 | 861.25 |  | 1378 |  | 2239.25 | [9 empty] | 4 | 689 | 8 | 1378
| Splash block | 8 | ea |  |  | 16 | 280 |  | 400 |  | 680 | [9 empty] | 80 | 640 |  | 680
Concrete Accessories
| Expansion/Contraction Joint Filler ASTM D1751 or ASTM D1752 Type I or Type II. Material must be 13 mm thick, unless otherwise indicated. | 100 | lm |  |  | 12 | 150 |  | 850 |  | 1000 | [9 empty] | 3 | 300 | 30 | 3000
| Expansion joint/Isolation Joint between Slab and Wall x Slab depth 270mm (detail 6/SS-502 & 7/SS-502) | 73 | lm |  |  | 32 | 109.5 |  | 474.5 |  | 584 | [9 empty] | 4.5 | 328.5 | 30 | 2190
| Allowance for Control joint | 63 | lm |  |  | 8 | 94.5 |  | 409.5 |  | 504 | [9 empty] | 2 | 126 | 30 | 1890
Concrete Curing
| Provide concrete curing material in accordance with ACI 301 Section 5 and ACI 308.1 Section 2. | 216 | m2 |  |  | 2 |  |  | 648 |  | 648 | [9 empty] | 2 | 432 | 4 | 864
Sundries
| Concrete lintel including reinforcement, formwork etc., complete all in accordance with drawings and specification | 8 | lm |  |  | 2 | 96 | 8 | 96 |  | 200 | [9 empty] | 22 | 176 | 40 | 320
Construct CMU Demonstration Building
Concrete Masonry Unit
CMU walls with bond beam and required steel reinforcement, jointed and pointed in cement and sand mortar including all crack control joints, anchors, steel angle, metal laths, fire/smoke resistive joints, wall ties; all in accordance with the drawing and specification.
| 200mm CMU | 308 | m2 |  |  | 252 | 3080 | 100 | 1601.6 |  | 4781.6 |  |  |  | 21 | 6468 |  |  |  |  | 6 | 1848 | 40 | 12320
THERMAL AND MOISTURE PROTECTION
Specification Section 07 14 00
Fluid-Applied Waterproofing
Substructure
| Fibrated emulsion-based dampproofing shall be cold-applied type conforming to ASTM D1227 Type II, Class 1, asbestos-free | 573 | m2 |  |  | 48 | 573 |  | 2005.5 |  | 2578.5 | [9 empty] | 1 | 573 | 7 | 4011
Specification Section 07 21 13
| Steel Structure Building |  |  |  |  | 560 | 5000 | 10000 | 15000 |  | 30000 | [10 empty] | 13719 |  | 30000
Roof and Deck Insulation
supply and installation of rigid insulation to roof on top of structural metal decking with necessary supports, plates, purlins, bolts, anchors, struts and all other fittings to complete the work all in accordance with drawings and specification Exterior Walls U = 0.57 W/M2K Roof Assemblies U = 0.44 W/M2K
Roof Accessories
| Allow for prefinish roofedge flashing | 1 | Item | [7 empty] | inc | [5 empty] | 27960 | 27960 | 65000 | 65000 | 1500 | 1500
| painted plywood fascia 19mmx300mm | 1 | Item | [7 empty] | inc | [5 empty] | inc |  | inc |  | 1200 | 1200
Specification Section 07 42 63
Fabricated Wall Metal Assemblies
D | Supply and Install insulated wall panel including accessories for a complete weather-tight wall system. All in accordance with the drawings and specification | 23 | m2 | [7 empty] | inc | [5 empty] | inc |  | inc |  | 95 | 2185
| Standing seam metal roof | 146 | m2 | [7 empty] | inc | [5 empty] | inc |  | inc |  | 42 | 6132
| downspout | 31 | lm | [7 empty] | inc | [5 empty] | inc |  | inc |  | 22 | 682
| Gutters | 23 | lm | [7 empty] | inc | [5 empty] | inc |  | inc |  | 25 | 575
| Prefinished metal ridge cap | 12 | lm | [7 empty] | inc | [5 empty] | inc |  | inc |  | 25 | 300
Specification Section 08 11 13
Steel Doors and Frames
Supply and installation of hollow metal doors including finishes, magnetic weatherstripping, frame, sub frame, fixings, fittings, accessories etc. complete; all in accordance with drawings and specification.
External
| Type B - Solid Core Hollow Metal door and frame, stained door and painted frame, size:900x2100mm, thk 45mm | 4 | ea |  |  | 16 | 200 | 80 | 3120 |  | 3400 | [7 empty] | 500 | 2000 | 1200 | 4800 |  | 3400
| Type A - Solid Core Hollow Metal double door and frame, painted, size: 900x2100mm, thk 45mm | 2 | ea |  |  | 8 | 100 | 40 | 1440 |  | 1580 | [7 empty] | 400 | 800 | 1200 | 2400 |  | 1580
Specification Section 08 71 00
Door Hardware
Supply and installation of door hardware set including necessary fixings and fittings, finishes, accessories etc. complete; all in accordance with drawings and specification.
| SET 1: 1-1/2 PR hinges 1 Passage lock with leveler, stainless steel satin 1 EA door closer, C02061, low resistance 1 Set scilencers | 4 | ea |  |  | 16 | 160 |  | 1680 |  | 1840 | [5 empty] | inc |  | inc |  | 450 | 1800 |  | 1840
| SET 2: (Main entry / Exit) 3 PR hinges 1 Leaf exit device, grade 1 1 EA entry lock set, stainless steel satin 2 EA door closer, C02061, low resistance 1 EA Threshold J32130 1 Set weather seals | 2 | ea |  |  | 8 | 80 |  | 1200 |  | 1280 | [5 empty] | inc |  | inc |  | 600 | 1200 |  | 1280
Specification Section 09 22 16
Non Structural Metal Framing
| Supply and Install steel truss with MC purlin and gusset plate with bolts with min 75mm clear spacing to edge of plate or member and a max. of 150mm between bolts, as indicated in the drawing | 1 | item | [7 empty] | inc | [7 empty] | inc |  | 800 | 800
| 150mmx28mmx600mm embed plate with (2) 16mmx125mm welded stud at 250 oc. Align plate with cl of steel truss | 23 | lm | [7 empty] | inc | [7 empty] | inc |  | 15 | 345
FINISHES
Specification Section 09 23 00
Plastering
Supply and applying of plaster; all in accordance with drawings and specification
| Interior Plastering h=2.65m | 218 | m2 |  |  | 200 | 1308 | 327 | 1308 |  | 2943 |  |  |  | 16 | 3488 |  |  |  |  | 4 | 872 | 15 | 3270
| Exterior Plastering h=4.4m | 308 | m2 |  |  | 240 | 1848 | 462 | 3080 |  | 5390 |  |  |  | 20 | 6160 |  |  |  |  | 6 | 1848 | 20 | 6160
Flooring
Supply and applying of floor coating; all in accordance with drawings and specification
| Epoxy Sealer to Concrete Floor | 150 | m2 |  |  | 24 | 225 |  | 1200 |  | 1425 |  |  |  | 11 | 1650 |  |  |  |  | 3 | 450 | 15 | 2250
| Threshold for entrance door (included also in Hardware set, price only once) | 2 | unit |  |  | 3 | 30 |  | 70 |  | 100 | [9 empty] | 22 | 44 | 20 | 40
Acoustic Tile
| ACT - Acoustical ceiling tiles fines fissured, squared laid-in, white, size: 300x600mm | 35 | m2 |  |  | 16 | 280 | 35 | 1137.5 |  | 1452.5 |  |  |  | 38 | 1330 |  |  |  |  | 17 | 595 |  | 1452.5
Skirting Finishes
| Type Epoxy | 82 | lm |  |  | 24 | 369 |  | 164 |  | 533 |  |  |  | 7 | 574 |  |  |  |  | 5 | 410 | 7.5 | 615
Wall Finishes
Specification Section 09 90 00
Paints and Coatings
| Interior To receive paint | 289.068 | m2 |  |  | 24 | 1734.408 |  | 1156.272 |  | 2890.68 |  |  |  | 8 | 2312.544 |  |  |  |  | 5 | 1445.34 | 15 | 4336.02
| Exterior To received 2 coats enamel paint | 306.68 | m2 |  |  | 32 | 1840.08 |  | 3680.16 |  | 5520.24 |  |  |  | 15 | 4600.2 |  |  |  |  | 8 | 2453.44 | 15 | 4600.2
Sundries
Exposed Area
| Type OTS, Open to structure with paint | 115 | m2 |  |  | 16 | 690 |  | 460 |  | 1150 | [9 empty] | 3 | 345 |  | 1150
MECHANICAL SYSTEM
Fire protection
Supply ,install,test & commissioning of Fire extinguishers as per the project documents
| 4.5 kg ABC fire extinguisher with brakcet | 2 | No |  |  | 2 | 50 |  | 500 |  | 550 | [9 empty] | 380 | 760 |  | 550
Exhaust Fan
Supply ,install,test & commissioning of Exhaust Fan as per the project documents
| EF-01 | 1 | No |  |  | 2 | 50 |  | 180 |  | 230 | [9 empty] | 15 | 15 |  | 230
LVF Fan
Supply ,install,test & commissioning of LVF Fan as per the project documents
| LVF-01 | 1 | No |  |  | 1 | 100 |  | 2000 |  | 2100 | [9 empty] | 80 | 80 |  | 2100
Registers
Supply ,install,test & commissioning of registers as per the project documents
| EG-01 | 1 | No |  |  | 16 | 200 |  | 1500 |  | 1700 | [9 empty] | 850 | 850 |  | 1700
ELECTRICAL SYSTEM
Switchgear
Supply ,install,test & commissioning of switchgear as per the project documents
| LP | 1 | No |  |  | 4 | 100 |  | 250 |  | 350 | [9 empty] | 250 | 250 |  | 350
Wiring Accessories
Supply ,install,test & commissioning of wiring accessores as per the project documents
| 16A,220V,50Hz ,type F,duplex receptacle | 4 | No |  |  | 8 | 45 |  | 160 |  | 205 | [9 empty] | 65 | 260 |  | 205
| Manual motor rated switch with thermal protection | 2 | No |  |  | 5 | 30 |  | 250 |  | 280 | [9 empty] | 40 | 80 |  | 280
Light fittings
Supply ,install,test & commissioning of light fittings as per the project documents
| Type A | 6 | No |  |  | 6 | 18 |  | 360 |  | 378 | [9 empty] | 15 | 90 |  | 378
| Type AE | 2 | No |  |  | 2 | 6 |  | 120 |  | 126 | [9 empty] | 15 | 30 |  | 126
| Type B | 2 | No |  |  | 2 | 6 |  | 120 |  | 126 | [9 empty] | 15 | 30 |  | 126
| Type CE | 2 | No |  |  | 2 | 6 |  | 120 |  | 126 | [9 empty] | 15 | 30 |  | 126
| Type X | 2 | No |  |  | 2 | 6 |  | 120 |  | 126 | [9 empty] | 15 | 30 |  | 126
Switches
Supply ,install,test & commissioning of switches as per the project documents
| Three way switch | 2 | No |  |  | 2 | 6 |  | 70 |  | 76 | [9 empty] | 12 | 24 |  | 76
Point wiring
Supply ,install,test & commissioning of wires and conduits as per the project documents
| Power connection | 6 | No |  |  | 6 | 90 |  | 90 |  | 180 | [9 empty] | 22 | 132 |  | 180
| Light fittings | 14 | No |  |  | 6 | 210 |  | 252 |  | 462 | [9 empty] | 8 | 112 |  | 462
| Switch points | 2 | No |  |  | 2 | 30 |  | 30 |  | 60 | [9 empty] | 10 | 20 |  | 60
Lightening protection system
Supply ,install,test & commissioning of lightening protection system as per the project documents
| Roof conductor | 64 | m |  |  | 16 | 320 |  | 512 |  | 832 | [9 empty] | 4 | 256 |  | 832
| Air terminal | 10 | No |  |  | 16 | 50 |  | 120 |  | 170 | [9 empty] | 8 | 80 |  | 170
| Down conductor with 25 mm protective conduit | 24 | m |  |  | 8 | 120 |  | 207 |  | 327 | [9 empty] | 5 | 120 |  | 327
Grounding system
Supply ,install,test & commissioning of grounding system as per the project documents
| Bond 50 mm2 bare copper wire | 17 | m |  |  | 8 | 85 |  | 425 |  | 510 | [9 empty] | 18 | 306 |  | 510
| 50 mm2 bare copper copper ground ring,760 mm below grade ,1.5 m from building | 69 | m |  |  | 24 | 690 |  | 2760 |  | 3450 | [9 empty] | 32 | 2208 |  | 3450
| 10 mm2 bare copper ground wire between main panel LP & ground bar | 10 | m |  |  | 8 | 50 |  | 250 |  | 300 | [9 empty] | 3 | 30 |  | 300
| Ground rod | 13 | No |  |  | 8 | 195 |  | 1950 |  | 2145 | [9 empty] | 85 | 1105 |  | 2145
| Ground rod with inspection well | 1 | No |  |  | 1 | 15 |  | 250 |  | 265 | [9 empty] | 95 | 95 |  | 265
| Ground Bar | 1 | No |  |  | 1 | 15 |  | 120 |  | 135 | [9 empty] | 85 | 85 |  | 135
Site electrical
Supply ,install,test & commissioning of site electrical as per the project documents
| 25 mm PVC sch 40 conduit with CAP | 1.5 | m |  |  | 2 | 3 |  | 9 |  | 12 | [9 empty] | 5 | 7.5 |  | 12
0005AD | Survey & Design for Sitework in Support of the CMU Demonstration Building in Accordance with the Contract Documents | [9 empty] | 34000 | [10 empty] | 24000 |  | 36000
| Site survey and design | 4000 | m2 |  |  | 128 | 12000 | 2000 | 4000 |  | 18000 | [9 empty] | 3 | 12000 | 4 | 16000
| Graging of the area around building | 4000 | m2 |  |  | 280 | 6000 | 10000 |  |  | 16000 | [9 empty] | 3 | 12000 | 5 | 20000
0005AE | Construct Sitework in Support of the CMU Demonstration Building in Accordance with the Contract Documents | [9 empty] | 29447 | [10 empty] | 17967 |  | 36430
| Sitework construction needed (compaction) | 1 | item |  |  | 24 |  |  |  |  | 3000 | [9 empty] | 1500 | 1500 |  | 1500
Aggregate Pavement Section
A | Subgrade preparation | 998 | m2 |  |  | 72 | 1996 | 1996 |  |  | 3992 | [9 empty] | 3 | 2994 | 5 | 4990
C | 150mm Aggregate Base Course | 998 | m2 |  |  | 72 | 1497 | 499 | 16966 |  | 18962 | [9 empty] | 4.5 | 4491 | 15 | 14970
D | 300mm Compacted Subgrade | 998 | m2 |  |  | 72 | 1996 | 1497 |  |  | 3493 | [9 empty] | 9 | 8982 | 15 | 14970
0005AF | VAT Taxes (CLINS 0005AA-0005AE) | [9 empty] | 29128.2294 | [10 empty] | 27011.4162 |  | 37733.0491
0006 | CMU Demonstration Bldg. Access Road Aggregate in Accordance with the Contract Documents | [9 empty] | 4154.175 | [10 empty] | 4652.676 |  | 2492.505
0006AA | CMU Demonstration Bldg. Access Road Aggregate in Accordance with the Contract Documents | [9 empty] | 3742.5 | [10 empty] | 4191.6 |  | 2245.5
The Contractor is referred to the specification and drawings for all details related to the works of this division and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the items
Specification Section 32 12 15.00
Proposed Access Road
Aggregate Pavement Section
B | 150mm Aggregate Surface Course | 149.7 | m3 |  |  | 72 | 299.4 | 299.4 | 3143.7 |  | 3742.5 | [9 empty] | 28 | 4191.6 | 15 | 2245.5
0006AB | VAT Taxes (CLIN0006AA) | [9 empty] | 411.675 | [10 empty] | 461.076 |  | 247.005
| Total Excluding VAT | [5 empty] | 60549.6409 |  |  |  | 268544.5854 | [10 empty] | 249749.9288 |  | 345273.2192
| DBA (10%) | [5 empty] | 6054.9641

## BASE BID (2)
PROJECT :TRAINING CENTER
BILL OF QUANTITIES | [5 empty] | Price Breakdown
ITEM REF. | DESCRIPTION | QUANTITY | UNIT | RATE | AMOUNT | LABOUR MANHOURS | DIRECT LABOR COST | DIRECT EQUIPMENT COST | DIRECT MATERIALS COST | TOTAL DIRECT COST | OVERHEAD/ INDIRECT COST | PROFIT | TOTAL PROPOSED COST | RATE | AMOUNT
Base BID
0001 | Mobilization and Demobilization at the Concrete Maintenance Pad Area in Accordance with the Contract Documents
0001AA | Mobilization at the Concrete Maintenance Pad Area in Accordance with the Contract Documents | 1 | LS
0001AB | Demobilization at the Concrete Maintenance Pad Area in Accordance with the Contract Documents | 1 | LS
The Contractor is referred to the specification and drawings for all details related to the works of this division and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the items
0002 | Concrete Maintenance Pad Construction in Accordance with the Contract Documents
Construct concrete Maintenance Pad
A | Subgrade preparation | 480 | m2
B | 150mm Portland Cement Concrete | 65.4 | m3
C | 150mm Aggregate Base Course | 436 | m2
D | 300mm Compacted Subgrade | 436 | m2
E | Allowance for excavation | 480 | m2
Concrete Accessories
Dowel to Construction Joint
A | Allowance for Epoxy coated Dowel bar dia. 19 bar x 400mm length @ 300mm c/c in PCC 150mm thick (drawing ref CS502), sawcut 3mm per 50mm thick | 292 | unit
B | Thickened edge | 22 | unit
C | Contraction Joint | 90 | lm
0003 | Concrete Maintenance Pad Area Sitework in Accordance with the Contract Documents
0003AA | Survey & Design for all Sitework Related to the Concrete Maintenance Pad Area in Accordance with the Contract Documents
| Survey & Design for all Sitework Related to the Concrete Maintenance Pad Area | 4000 | M2
| Grading of external area | 4000 | M2
0003AB | Construct Concrete Maintenance Pad Area Sitework in Accordance with the Contract Documents
Specification Section 32 12 15.00
Proposed Access Road
Aggregate Pavement Section
A | Subgrade preparation | 525 | m2
B | 150mm Aggregate Surface Course | 79 | m3
C | 150mm Aggregate Base Course | 525 | m2
D | 300mm Compacted Subgrade | 525 | m2
Additionals (with mobilization)
| Allowance for Generator | 1 | item
| Allowance for required water tank | 1 | item
| Allowance for External Fences | 1 | item
Total CLINs 0001-0003 without VAT
0004 | VAT Taxes (CLINS 0001-0003)
Carried to Collection

## Option 2 (2)
PROJECT :TRAINING CENTER
BILL OF QUANTITIES | [5 empty] | Price Breakdown
ITEM REF. | DESCRIPTION | QUANTITY | UNIT | RATE | AMOUNT | LABOR MAN-HOURS | DIRECT LABOR COST | DIRECT EQUIPMENT COST | DIRECT MATERIALS COST | TOTAL DIRECT COST | OVERHEAD/ INDIRECT COST | PROFIT | TOTAL PROPOSED COST | RATE | AMOUNT
OPTION BID
0005 | CMU Demonstration Building & Site Construction in Accordance with the Contract Documents
The Contractor is referred to the specification and drawings for all details related to the works of this division and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the items
0005AA | Mobilization
0005AA | Mobilization at the CMU Demonstration Building Area in Accordance with the Contract Documents | 1 | LS
0005AB | Demobilization
0005AB | Demobilization at the CMU Demonstration Building Area in Accordance with the Contract Documents | 1 | LS
0005AC | CMU Demonstration Building Construction in Accordance with the Contract Documents
Construct CMU Demonstration Building
Construct Concrete Slab
Excavation
A | Excavation for foundation; all in accordance with the drawings and specification | 324 | m3
Disposal
B | Disposal of excavated surplus material from site to approved location all in accordance with the drawings and specification | 178 | m3
Backfilling
C | Backfilling in making up levels with selected excavated materials; in compliance with the Specification and subject to the Contracting Officer's approval | 216 | m3
Shoring
G | Shore the existing surface prior to excavation, including to retain a Professional Engineer, Finish shoring, including sheet piling, and install as necessary to protect workmen, banks, adjacent paving, structures, and utilities | 82.05 | m2
Capillary Barrier Base Material
E | 200mm thick crushed stone capillary barrier min 760mm all in accordance with the drawings and specification | 124.64 | m3
F | 100mm thick capillary vapor barrier all in accordance with the drawings and specification | 16.4 | m3
Anti-Termite Treatment
G | Anti-termite treatment all in accordance with the drawings and specification | 280 | m2
Dewatering
H | Allowance for installation and maintenance of Dewatering System | 30 | day
CONCRETE WORKS
The Contractor is referred to the specification and drawings for all details related to the works of this division and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the items
SUBSTRUCTURE
SECTION 03 30 00
Cast-in Place Concrete
Reinforced concrete 28 Mpa, design mix as per the drawings and specification ( General notes 3 drawing ref SB100)
A | Footing | 58.5 | m3
B | Foundation Stem Wall | 10.5138 | m3
C | 150mm Thick Slab | 24.6 | m3
D | Concrete stoop size:2100x400mm | 2 | ea
Concrete Reinforcing
Reinforcing steel deformed bars of all diameters, ASTM A615, Grade 460 UNO, all in accordance with the drawings and specification. ( General notes 2 drawing ref SB100)
| T16 Reinforcing bars diameters in Footing | 1150 | kg
| T16 Reinforcing bars diameters in Stem Wall | 410 | kg
| Reinforcing bars diameters Ø16 BAR AT 450mm O.C. EACH WAY, CENTERED IN SLAB | 1470 | kg
Structural Cast-in-Place Concrete Forming
Formwork all in accordance with the drawings and specification.
| To Footings | 306 | m2
| To stem walls | 94.94 | m2
| To slab | 172.25 | m2
| Splash block | 8 | ea
Concrete Accessories
| Expansion/Contraction Joint Filler ASTM D1751 or ASTM D1752 Type I or Type II. Material must be 13 mm thick, unless otherwise indicated. | 100 | lm
| Expansion joint/Isolation Joint between Slab and Wall x Slab depth 270mm (detail 6/SS-502 & 7/SS-502) | 73 | lm
| Allowance for Control joint | 63 | lm
Concrete Curing
| Provide concrete curing material in accordance with ACI 301 Section 5 and ACI 308.1 Section 2. | 216 | m2
Sundries
| Concrete lintel including reinforcement, formwork etc., complete all in accordance with drawings and specification | 8 | lm
Construct CMU Demonstration Building
Concrete Masonry Unit
CMU walls with bond beam and required steel reinforcement, jointed and pointed in cement and sand mortar including all crack control joints, anchors, steel angle, metal laths, fire/smoke resistive joints, wall ties; all in accordance with the drawing and specification.
| 200mm CMU | 308 | m2
THERMAL AND MOISTURE PROTECTION
Specification Section 07 14 00
Fluid-Applied Waterproofing
Substructure
| Fibrated emulsion-based dampproofing shall be cold-applied type conforming to ASTM D1227 Type II, Class 1, asbestos-free | 573 | m2
Specification Section 07 21 13
Steel Structure Building
Roof and Deck Insulation
supply and installation of rigid insulation to roof on top of structural metal decking with necessary supports, plates, purlins, bolts, anchors, struts and all other fittings to complete the work all in accordance with drawings and specification Exterior Walls U = 0.57 W/M2K Roof Assemblies U = 0.44 W/M2K
Roof Accessories
| Allow for prefinish roofedge flashing | 1 | Item
| painted plywood fascia 19mmx300mm | 1 | Item
Specification Section 07 42 63
Fabricated Wall Metal Assemblies
D | Supply and Install insulated wall panel including accessories for a complete weather-tight wall system. All in accordance with the drawings and specification | 23 | m2
| Standing seam metal roof | 146 | m2
| downspout | 31 | lm
| Gutters | 23 | lm
| Prefinished metal ridge cap | 12 | lm
Specification Section 08 11 13
Steel Doors and Frames
Supply and installation of hollow metal doors including finishes, magnetic weatherstripping, frame, sub frame, fixings, fittings, accessories etc. complete; all in accordance with drawings and specification.
External
| Type B - Solid Core Hollow Metal door and frame, stained door and painted frame, size:900x2100mm, thk 45mm | 4 | ea
| Type A - Solid Core Hollow Metal double door and frame, painted, size: 900x2100mm, thk 45mm | 2 | ea
Specification Section 08 71 00
Door Hardware
Supply and installation of door hardware set including necessary fixings and fittings, finishes, accessories etc. complete; all in accordance with drawings and specification.
| SET 1: 1-1/2 PR hinges 1 Passage lock with leveler, stainless steel satin 1 EA door closer, C02061, low resistance 1 Set scilencers | 4 | ea
| SET 2: (Main entry / Exit) 3 PR hinges 1 Leaf exit device, grade 1 1 EA entry lock set, stainless steel satin 2 EA door closer, C02061, low resistance 1 EA Threshold J32130 1 Set weather seals | 2 | ea
Specification Section 09 22 16
Non Structural Metal Framing
| Supply and Install steel truss with MC purlin and gusset plate with bolts with min 75mm clear spacing to edge of plate or member and a max. of 150mm between bolts, as indicated in the drawing | 1 | item
| 150mmx28mmx600mm embed plate with (2) 16mmx125mm welded stud at 250 oc. Align plate with cl of steel truss | 23 | lm
FINISHES
Specification Section 09 23 00
Plastering
Supply and applying of plaster; all in accordance with drawings and specification
| Interior Plastering h=2.65m | 218 | m2
| Exterior Plastering h=4.4m | 308 | m2
Flooring
Supply and applying of floor coating; all in accordance with drawings and specification
| Epoxy Sealer to Concrete Floor | 150 | m2
| Threshold for entrance door (included also in Hardware set, price only once) | 2 | unit
Acoustic Tile
| ACT - Acoustical ceiling tiles fines fissured, squared laid-in, white, size: 300x600mm | 35 | m2
Skirting Finishes
| Type Epoxy | 82 | lm
Wall Finishes
Specification Section 09 90 00
Paints and Coatings
| Interior To receive paint | 289.068 | m2
| Exterior To received 2 coats enamel paint | 306.68 | m2
Sundries
Exposed Area
| Type OTS, Open to structure with paint | 115 | m2
MECHANICAL SYSTEM
Fire protection
Supply ,install,test & commissioning of Fire extinguishers as per the project documents
| 4.5 kg ABC fire extinguisher with brakcet | 2 | No
Exhaust Fan
Supply ,install,test & commissioning of Exhaust Fan as per the project documents
| EF-01 | 1 | No
LVF Fan
Supply ,install,test & commissioning of LVF Fan as per the project documents
| LVF-01 | 1 | No
Registers
Supply ,install,test & commissioning of registers as per the project documents
| EG-01 | 1 | No
ELECTRICAL SYSTEM
Switchgear
Supply ,install,test & commissioning of switchgear as per the project documents
| LP | 1 | No
Wiring Accessories
Supply ,install,test & commissioning of wiring accessores as per the project documents
| 16A,220V,50Hz ,type F,duplex receptacle | 4 | No
| Manual motor rated switch with thermal protection | 2 | No
Light fittings
Supply ,install,test & commissioning of light fittings as per the project documents
| Type A | 6 | No
| Type AE | 2 | No
| Type B | 2 | No
| Type CE | 2 | No
| Type X | 2 | No
Switches
Supply ,install,test & commissioning of switches as per the project documents
| Three way switch | 2 | No
Point wiring
Supply ,install,test & commissioning of wires and conduits as per the project documents
| Power connection | 6 | No
| Light fittings | 14 | No
| Switch points | 2 | No
Lightening protection system
Supply ,install,test & commissioning of lightening protection system as per the project documents
| Roof conductor | 64 | m
| Air terminal | 10 | No
| Down conductor with 25 mm protective conduit | 24 | m
Grounding system
Supply ,install,test & commissioning of grounding system as per the project documents
| Bond 50 mm2 bare copper wire | 17 | m
| 50 mm2 bare copper copper ground ring,760 mm below grade ,1.5 m from building | 69 | m
| 10 mm2 bare copper ground wire between main panel LP & ground bar | 10 | m
| Ground rod | 13 | No
| Ground rod with inspection well | 1 | No
| Ground Bar | 1 | No
Site electrical
Supply ,install,test & commissioning of site electrical as per the project documents
| 25 mm PVC sch 40 conduit with CAP | 1.5 | m
0005AD | Survey & Design for Sitework in Support of the CMU Demonstration Building in Accordance with the Contract Documents
| Site survey and design | 4000 | m2
| Graging of the area around building | 4000 | m2
0005AE | Construct Sitework in Support of the CMU Demonstration Building in Accordance with the Contract Documents
| Sitework construction needed (compaction) | 1 | item
Aggregate Pavement Section
A | Subgrade preparation | 998 | m2
C | 150mm Aggregate Base Course | 998 | m2
D | 300mm Compacted Subgrade | 998 | m2
0005AF | VAT Taxes (CLINS 0005AA-0005AE)
0006 | CMU Demonstration Bldg. Access Road Aggregate in Accordance with the Contract Documents
0006AA | CMU Demonstration Bldg. Access Road Aggregate in Accordance with the Contract Documents
The Contractor is referred to the specification and drawings for all details related to the works of this division and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the items
Specification Section 32 12 15.00
Proposed Access Road
Aggregate Pavement Section
B | 150mm Aggregate Surface Course | 149.7 | m3
0006AB | VAT Taxes (CLIN0006AA)
Total Excluding VAT